## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Sourcing
Research software configuration options for restaurants | https://www.cuboh.com/blog/restaurant-tablet-best-practices https://www.business.com/articles/best-tablet-uses-restaurants/
Generate quotes and review costs
Choose system and review timeline
Incorporate disability standards
Install equipment
Hire electrician to wire the tables
Wire and install equipment at tables in the bar at the Downtown and North restaurant locations.
Evaluate if we even require the tables to be wired | https://www.business.com/articles/best-tablet-uses-restaurants/
Power up tablets and printers
Complete setup and security requirements
Install and configure software
Hire company to design tablet version of branding, design and upload | maybe our website company can handle this? Otherwise, Seydou recommends Terrific Tablets
Install software to tablets, kitchen and back office
Configure tablets with menu and prices, allergens, and nutrition
Configure software to allow back end customization, promotions and features.
Run testing, and optomize
Food wastage
Gather historical data of comps
Determine if this is a fair representation of food waste
Create a plan to reduce food waste
Measure results to determine if the food waste has been reduced
Onboarding
Hold a meeting with wait staff to get their buy in
Determine if tips will be impacted since the amount of service is reduced
Training
Create a written training manual
Train GMs on new software
Train FOH staff and BOH staff on new software
Test run ordering system
Create troubleshoot/support plan
Run a test day with friends and family |  |  |  |  | Gilly for North, Nia for Waterfront and
Launch
Plan launch, staffing, execution
Launch
Feedback
Implement a post-dining survey to assess customer satisfaction
Evalute metrics

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: All vendors selected and secured
Research software configuration options for restaurants | https://www.cuboh.com/blog/restaurant-tablet-best-practices https://www.business.com/articles/best-tablet-uses-restaurants/ | 5 | 2 | 3 | 4 | H
Confirm if existing software system will operate with the new software |  | 5 | 2 | 3 | 4 | M
Choose software system and review timeline |  | 3 | 2 | 3 | 4 | H
Choose final configuration of hardware for foh, boh and office |  | 3
Hire electrician to wire the tables |  | 1
Hire company to design tablet version of branding, design and upload | maybe our website company can handle this? Otherwise, Seydou recommends Terrific Tablets | 2
Generate quotes and finalize costs |  | 2
Create vendor contracts, meet and sign documents |  | 3
Order and ship hardware and equipment |  | 7
Milestone: Hardware Installation complete
Wire and install equipment at tables in the bar at the Downtown and North restaurant locations. Low conf, never wired for tablets to tables |  | 4 | 4 | 5 | 6 | L
Install hardware in BOH and office |  | 3
Power up tablets and printers |  | 1
Complete setup and security requirements |  | 1
Milestone: Software ready
Install chosen software |  | 9 | 7 | 9 | 10 | H
upgrade the POS system if running older version *never done before, low conf |  | 4 | 4 | 8 | 12 | L
Upload menu, branding and coupon values | Carter wants to revamp his menu | 10 | 7 | 10 | 14 | M
Configure tablets with menu and prices, allergens, and nutrition |  | 12
Configure software to allow back end customization, promotions and features. |  | 12
Run testing, and optimize |  | 2
Milestone: Metrics to evaluate food waste ready
Gather historical data of comps |  | 2
Determine if this is a fair representation of food waste |  | 1
Create a plan to reduce food waste |  | 1
Milestone: Ready to go live on test clients
Hold a meeting with wait staff to get their buy in* critical |  | 1 | 1 | 2 | 3 | L
Preparations and planning for trainings |  | 7 | 6 | 7 | 8 | m
Pre-train meeting to introduce tablets and changes to staff (separate, x 2) |  | 2 | 2 | 3 | 4 | L
Create a written training manual |  | 3 | 2 | 3 | 4
Train GMs on new software (Seydou)(separate, x 2) |  | 1 | 1 | 2 | 3
Train on back end operations, ie coupon or availability configuration to computer in office |  | 2 | 1 | 2 | 3
Train FOH staff and BOH staff on new software (GM train, 2 hours, plus 1 hr before and after for facilitator and debrief)(separate, x 2), low conf, never done |  | 3 | 2 | 3 | 4 | H
Test run ordering system |  | 2
Create troubleshoot/support plan |  | 5
Milestone: Launch
Run a test day with friends and family |  | 1 |  |  | Gilly for North, Nia for Waterfront and
Plan launch, staffing, execution |  | 7
Milestone: Feedback
Implement a post-dining survey to assess customer satisfaction |  | 1
Evalute metrics |  | 1

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
https://www.cuboh.com/blog/restaurant-tablet-best-practices
https://www.business.com/articles/best-tablet-uses-restaurants/

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction | 8 minutes for appetizers and 12-15 minutes for entrees | Is customer service more efficient? | Order tickets | FALSE
Customer Satisfaction | Check out time of one min or less | Is the checkout experience more efficient? | check out time one minute or less | FALSE
Customer Satisfaction | Tech issues >5% reported | Less than 5% of customers who use tablets report technical issues each week | Tech issue reports | FALSE
Accuracy | Order accuracy | 98% order accuracy | Order accuracy for tablets vs server | FALSE
Effeciency | Lobby wait time | Customers wait, on average, less than 10 minutes | Reported wait times | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Question Answer Options (depends on question type)
Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Have you visited this restaurant before?
How many people were in your party?
Was the tablet easy to use?
Did you enjoy the tablet experience during a restaurant visit? | Yes/No | Yes | No
Was it easy to pay and check out? | Yes/No | Yes | No
Did you have any technical issues or limitations while using the tablet? | Yes/No | Yes | No
Did the features and promotions on the tablet encourage you to order or try additional menu items? | Multiple choice | Yes, I took advantage of the bogo deal. | Yes, I took the mushroom and onion add on. | Yes, I chose the daily feature. | Yes, I took the dessert promotion. | No, I declined all offers.
What was your interaction with the server like as they answered questions and brought your order? | Open-ended | open-ended
Were you celebrating a special occasion? | Yes/No | Yes | No
Overall, on a scale of 1-5, 1 being the best, and 5 the worst, how would you rate the tablet experience? | Scaled | 1-very satisfied | 2-satisfied | 3-neutral | 4-dissatisfied | 5-very dissatisfied
Did you enjoy your meal? | Yes/No | Yes | No
How long did your dinner take tonight? | Multiple choice | It was fast! | It was average | It was too slow.
Would you recommend this restaurant to your friends and family? | Yes/No | Yes | No
Will you be back? | Yes/No | Yes | No